## Slide 1
自主創新
Innovation Ownership
綠能環保
Sustainable Energy
雲端服務
Cloud Service
無線寬頻
Mobile Broadband
新興市場
Emerging Market
RCTO TAA Plan
January 28th 2015

## Slide 2: Contents
Introduction and Overview
Key Milestone and High Level Process Flows
Capacity Plan
Factory Layout
Resource Plan

## Slide 3: TAA Introduction and Overview
Introduction
  TAA refers to the Trade Agreements Act
  TAA requires that the U.S. Government may acquire only “U.S. – made or designated country end products
Objective
  Establish a new factory in Taiwan to support HP TAA business
Scope and Target Date
  To support combination of other ODM platforms NB/Mobility
  Go Live Readiness by 1st June

## Slide 4: Key Milestone
The following key milestones are base on official kickoff by 1/30
2/2
3/16
4/27
5/11
4/20
6/1
Recruitment and Training
Pilot Run
HP Audit
UL Certificate
CSA Certificate
FCS
Factory Setup
5/25
5/18

## Slide 5: TAA Process Flow
Manufacture
Ship
Order Execution
HP
TAA Factory
Manufacture
Ship
Order Execution
Designated
Destination
HUB
Designated
Destination
Suppliers
ODM
Forecast/Order
Forecast/Order
Order
Materials
Materials/HALB
Forecast/Order
Forecast

## Slide 6
LCM
B/U
Keyparts
Diag. Test
Image download
Run-In
OA 3.0
Packing
Shipment
Assembly
2PP
Cosmetic
Cosmetic
Final Assembly Process Flow
Notes: 6

## Slide 7: Capacity Plan
Monthly capacity 15.8K per line
  8 hours a day, 5 days a week and 22 days a month
The capacity can be increased when order upside
  OT on weekday and Saturday When order between 15K~28K
  Dual line with OT on weekday and Saturday when order between 30K~55K

## Slide 8: Factory Layout
Office
WIP
Assembly Line
PA Line
Finish Goods
Finish Goods
Run-in
Run-in
4F
Elev.
Raw Material
Expensive Raw Material
Packing Material
Office
B1F
To 4F
Elev.
Total : 265 (m2)
Total : 440 (m2)
Raw material
Manufacturing
Finish Goods
B4F: 1765 M2
BB1F: 705 M2
Line 1
Line 2
From B1F

## Slide 9: Resource Plan
Hiring
Week 4/27
Week +2
Weeks +4
Mid of March
May
Training
Pilot run
On Board

## Slide 10: Thanks !
Questions and Answers
Notes: 10