## 3.5.
UPS kick-off questions tracker
Item | Questions | Answers | Status | PIC
1 | How UPS to settle the non EDI850 sample orders? BT orders | HP will check with WW team and get back to IEC. IEC smart PO and BT order sample as attached. | OPEN | HP
2 | Can UPS also cover the asset tag with static information | Yes, UPS can cover overall printing asset tags. | Close | HP
3 | Whether UPS cover the SKU with multiple asset tags and different locations? | Yes, UPS will release all asset tags according to AV in BOM. | Close | HP
4 | How long should we escalate the issue that no order information from UPS? | 4 hours. | Close | HP
5 | Could HP provide us the list, including all the possible information in AT, like MAC1#,UUID#... | HP will check and provide the list. | OPEN | HP
6 | If the information what we upload is not correct, we expect UPS can judge and alarm us. | Yes, UPSGetATRP will check the information to make sure it is correct. | Close | HP
7 | We need UPSGetATRP can release the template within 1m after we upload the correct information. | No problem, UPS can release the templates within 2s once receive the information from ODM. | Close | HP
8 | UPS asset tag# reflow process for both factory repair units and Hp high volume cancellation units. | HP will create UPSResetSN will be ready on /27. | Close | Bill/Chris
9 | Is it acceptable to reassign PO# for non shell order controlled by IEC shopfloor? | YES. Update the flow chart to make it more clearer. | Close | HP/IEC
10 | We need HP have 24h backup team to solve issues, else it will impact our manufacturing. | OK, no problem. | Close | HP
11 | If the shipment is delayed due to the UPS issue, can HP team help to engage HP factory Execution team together? | OK, no problem. | Close | HP
12 | After UPS cut in, our own bat process will be used anymore, means no any backup. | It would be soft cut from UPS AV showed in ATAN. IEC check whether it is OK and can production line exchange the FIS interface at the same station. XC: confirmed OK | Close | XC
13 | May I know whether UPSGetATRP will release the complete asset tag BTW file with all asset tag information to us so that we can print directly or UPS just release the asset tag blank template to us and we need add the information and create the complete asset tag in our shopfloor? | UPSGetATRP Provides: Information file with BTW data, Printer stock, SOP image. Option: Use UPSGetTags - provides BTW and data | Close | Bill/Chris
14 | Can UPS help to create the extra barcode for the asset tag without barcode itself so that we can achieve the systemic checking for this kind of asset tag. | BTW has a Barcode on unused portion of the tag If there is no barcode at all (In Development) • SN is printed Human readable and barcode on unused portion of the ta | Close | Bill/Chris
15 | HP wants to add UPSUpdateHPPO before going to UPSGetATRP, it is OK? | It is fine for us to add UPSUpdateHPPO for information upload. While, we would like to define where to load the factory information coz some information is created after image download and impossible to provide to UPSGetATM. | OPEN | HP/XC